## Report
GANTT CHART DRAFT 1 (01.02.2026)
Main Task | Sub Task | Contributor | Weeks
|  |  | 3 | [6 empty] | 4 | [6 empty] | 5 | [6 empty] | 6 | [6 empty] | 7
|  |  | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 22 | 23 | 24 | 25 | 26 | 27 | 28
|  |  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
A | Understand assignment | Adam | bar: 3 26
| Create Github | Kylie | bar: 3 27
| Assign Team Roles | Yexuan | bar: 3 26 to 3 28
| Review requirements & calculations | Yexuan | bar: 3 27 to 3 28
| Draft Problem statement | Tasin
| Identify testing requirements n evidance | Kylie & Tasin
B | 1. Construct an IPO Analysis for SWESMS (overall system) and at least TWO (2) key modules. | Adam, Tasin | bar: 3 26; 3 29
| 2. Clearly list all key inputs, processes, and outputs, including validations and calculations. | Yexuan | bar: 3 30
| 3. Provide brief justification for each IPO about why those inputs/processes/outputs are needed for SWESMS. | Kylie | bar: 3 31
| 4. Write the overall algorithm for the full system by showing proper in-details step-by-step and the menu loop until exit are chosen. | Tasin, Adam | bar: 3 1
C | 1. Write structured pseudocode for the full system and at least TWO (2) key modules. Your pseudocode must include selection, loops, and validation. | Adam,Kylie | bar: 4 3
| 2. Propose your program design including | Adam | bar: 4 4
| 3. Use draw.io to develop flowcharts using standard symbols for the following: | Yexuan | bar: 4 5
| 4. Based on your flowchart, provide brief explanations to justify them | Kylie | bar: 4 6
| review Code | Tasin | bar: 4 7
D | 1. Add equipment records such as ID, category, watts, max temp, maintenance interval, accumulated hours and any relevant information. | Adam | bar: 5 11
| 2. Update daily usage starts from 0–24 hours and current temperature must be in reasonable range with input validation. | Yexuan | bar: 5 12
| 3. Display all equipment with computed status: | Adam | bar: 5 13
| 4. Using the formula below to compute | Kylie | bar: 5 14
| 5. Alerts Generation by display alerts for: | Tasin | bar: 5 15
E | 1. Compare your flow chart diagrams with the final code. Explain how they align. | Adam | bar: 6 16
| 2. Identify at least TWO (2) improvements for implementation that can be done for the system. | Adam , Yexuan | bar: 6 17
| 3. Justify improvements based on user feedback or testing results. | Tasin or Kylie | bar: 6 18
| Prepare Presentation slides | ALL work tgt | bar: 6 19
| Peer to Peer | ALL work tgt | bar: 6 20
F | Rehearse system demo | Adam | bar: 6 21
| Explain calculation & logic | Yexuan | bar: 6 22
| Explain analysis & design | Tasin | bar: 7 22
| Present testing & screenshots | Kylie | bar: 7 23
| PRESENTATION ! ( finish ) | ALL work tgt | bar: 7 24
Adam | bar: 3 26
Kylie | bar: 3 26